## Project
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge 1 | In Charge 2 | Status | Actual | Updated | Update Details
1 | Login/Logout | Authentication | Staff, Instructor, Customer | User can login to use the function inside using google, facebook or using account that register | Tùng | Vinh | Done | iter1 | iter2
2 | Register | Authentication | Customer, Instructor | The register scrreen will pop up for the user to register, there wiil be 2 option to register by using google or facebook account | Tùng | Vinh | Done | iter2 | none
3 | Show courses | View | Customer | This is short descripiton for the screen/function (2-3 sentences) | Tùng | Vinh | Done | iter3 | none
4 | Add course to cart | Order | Customer | When user click add cart button, the course will be add to Cart List then will notification that the adding is successful | Thắng | Vinh | Done | iter4 | none
5 | Remove course from cart | Order | Customer | From cart, user can remove course from cart list if they don't want to payment for it. | Vinh | None | Done | iter5 | none
6 | Buy Course Now | Order | Customer | This is a button in the course screen, when user is clicked, customer will send to the checkout screen without come through cart and if user haven't login, it will send user to login screen then send back to checkout screen for payment | Tùng | Vinh | Status | iter6 | none
7 | Add Wishlist | Order | Customer | If user don't want to add cart or order now, user can add that course to wishlist and will order that course next time' | Thắng | Vinh | To Do | iter7 | none
8 | Remove Wishlist | Order | Customer | If user don't want that course tobe in wishlist for now, they can remove it from the wishlist' | Tùng | Hà | To Do | iter8 | none
9 | Show Cart | Order | Customer | When user click cart, a list will showup what course that user choisen | Vinh | Vinh | Done | iter9 | none
10 | Manage account | Management | Staff | Manage Account Staff | Hà | Thắng | To Do | iter10 | none
11 | Manage configuration | Management | Staff |  | Huy | Hà | To Do | iter11 | none
12 | Create statistics report | Management | Staff |  | Hà | Huy | To Do | iter12 | none
13 | Showcase learing progress | Customer | Customer |  | Vinh | Tùng | Done | iter13 | none
14 | Check out Cart | Order | Customer | This is a button when user click from cart list, the user will be send to check out screen for what they have add to cart' | Vinh | Vinh | Done | iter14 | none
15 | Ask for advice |  | Customer |  | Thắng | Vinh | To Do | iter15 | none
16 | Search Course | Search | Customer |  | Vinh | Hà | To Do | iter16 | none
17 | Fillter course by ratings | Search | Customer, Guest |  | Tùng | Huy | To Do | iter17 | none
18 | Filter course by price | Search | Customer, Guest |  | Hà | Thắng | To Do | iter18 | none
19 | Filter course by level | Search | Customer, Guest |  | Huy | Thắng | To Do | iter19 | none
20 | OTP Confirm login | Authentication | All | When guest use app's account to login, if the guest enter right username and password, system will send OTP using email to user to confirm login | Thắng | Tùng | Done | iter20 | none
21 | Forgot Password | Authentication | Customer | If the guest forgot their account, they will access forgot password option, the guest will enter the email that is use to register account, if the mail is correct, system will send an email that have OTP code to customer mail to confirm account and user will enter OTP, and popup screen to enter new password, else there will be an notification the email isn't in the system' | Tùng | Thắng | Done | iter21 | none
22 | Tranfer to another account | Authentication | Customer |  | Hà | Thắng | To Do | iter22 | none
23 | Login using Google | Authentication | Customer |  | Thắng | Vinh | Status | iter23 | none
24 | Login using Facebook | Authentication | Customer |  | Thắng | Huy | To Do | iter24 | none
25 | Schedule time to learn |  | Customer |  | Tùng | Thắng | To Do | iter25 | none
26 | Change UI Theme Light/Dark |  | All | User can setting application theme to dark theme or white to comfortable | Hà | Tùng | To Do | iter26 | none
27 | Manage courses |  | Instructor |  | Hà | Tùng | Done | iter27 | none
28 | Notification when not working for a long time |  | System |  | Huy | Vinh | To Do | iter28 | none
29 | Change UI Theme Light/Dark |  |  |  | Vinh | Tùng | To Do | iter29 | none
30 | Back up |  | System |  | Huy | Vinh | To Do | iter30 | none
31 | Notification when have new update from course |  | Customer |  | Hà | Tùng | To Do | iter31 | none
32 | Send notification when someone login to your account |  | System |  | Tùng | Huy | To Do | iter32 | none
33 | OTP when register on website |  | Customer |  | Vinh | Hà | To Do | iter33 | none
34 | Request Delete Account |  | Customer |  | Thắng | Vinh | To Do | iter34 | none
35 | Show Customer Learning |  | Customer | Customer can see course they have learned, when they clicked course | Vinh | Thắng | Done | iter35 | none
36 | Gift course to another user |  | Customer |  | Vinh | Huy | To Do | iter36 | none
37 | Show finished courses (Course Certification) |  | Customer | Xem khoa hoc da hoan thanh | Tùng | Thắng | Done | iter37 | none
38 | 30 days refund guarantee |  | Customer |  | Thắng | Vinh | To Do | iter38 | none
39 | Archive courses |  | Customer |  | Vinh | Tùng | Done | iter39 | none
40 | Disable account when wrong password over 5 times | Authentication | Customer, Instructor,Staff |  | Huy | Thắng | To Do | iter40 | none
41 | Publish course |  | Instructor |  | Huy | Vinh | Done | iter41 | none
42 | Facebook chat for support |  | Guest, Customer, Instructor |  | Hà | Thắng | To Do | iter42 | none
43 | Post announcement |  |  |  | Huy | Thắng | To Do | iter43 | none
44 | Q&A |  | Customer, Instructor |  | Vinh | Tùng | To Do | iter44 | none
45 | Restore Account | Authentication | Customer, Instructor | When an account is disable by wrong pass, an email will send to customer to repass and enable account again | Tùng | Vinh | To Do | iter45 | none
46 | Share course link |  | Customer, Instructor |  | Thắng | Hà | To Do | iter46 | none
47 | Send feedback teacher | Feedback/Report | Customer |  | Hà | Huy | To Do | iter47 | none
48 | Send Comment | Feedback/Report | Customer |  | Hà | Huy | To Do | iter48 | none
49 | Send report/feedback on system | Feedback/Report | Customer, Guest, Instructor, Staff |  | Tùng | Thắng | To Do | iter49 | none
50 | Report teacher | Feedback/Report | Customer |  | Tùng | Vinh | To Do | iter50 | none
51 | Send Cetification |  | System |  | Thắng | Vinh | Doing | iter51 | none
52 | Add user to the course |  | System |  | Huy | Tùng | Done | iter52 | none
53 | Paypal Payment | Order | Customer |  | None | Thắng | Done | iter53 | none
54 | Admin Dashboard | Dashboard | Admin |  | Huy | Vinh | Doing | iter54 | none
55 | Show comments on course | Customer |  |  | To Do | To Do | Done | iter55 | none
56 | Show course detail | Customer |  |  | To Do | To Do | Done | iter56 | none
57 |  |  |  |  | To Do | To Do | To Do | iter57 | none
58 |  |  |  |  | To Do | To Do | To Do | iter58 | none
59 |  |  |  |  | To Do | To Do | To Do | iter59 | none
60 |  |  |  |  | To Do | To Do | To Do | iter60 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4